## Project Tracker
Create a Project Tracker in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers, is in the About worksheet. | Project Tracker
The Start date can be manually input in cell D2, or use the template’s sample formula to find the smallest date in the milestone column from the milestone table below. |  | Start date: | 1/26/20201
The End date can be manually input in cell D3, or use the template’s sample formula to find the largest date in the milestone column from the milestone table below. |  | End date: | 2021-05-01
Information about the milestone table columns is in cells B4 to G4. | Enter a sequential set of numbers in the column below. | Enter the start date for the milestone or activity in the column below. | Enter the end date for the milestone or activity in the column below | Enter the milestone and/or activity description in the column below. This description will appear in the Project Chart.
Table headings are in cells B5 to G5. There are two hidden columns: The Start-on day and Task Duration columns in cells F5 and G5 are auto-calculated and used for creating the Gantt Chart in the Gantt Chart worksheet. Sample data is in cells B6 to E21. The next instruction is in cell A22. | Position | Start Date | End Date | Milestone/Activity
| 1 | 2021-01-20 | 2021-01-26 | Formation of groups and project selection pending approval.
| 2 | 2021-01-26 | 2021-02-01 | Project Requirements outlined and prepared and Preliminary designs implemented via robustness diagrams and flowcharts.
| 3 | 2021-02-01 | 2021-02-08 | Discussion and creation of project milestones and the shape of the final product solidified by the group and submitted.
| 4 | 2021-02-08 | 2021-02-15 | Determine and Format all project external library requirements and keep track of all api's required and test functionality.
| 5 | 2021-02-08 | 2021-02-22 | Design initial GUI for the application and begin laying out activities for every page and link that will be implemented in the app.
| 6 | 2021-02-20 | 2021-03-01 | Implement a strict and secure account login process and link the database that will store user information to the application. Test for vulnerabilities.
| 7 | 2021-02-25 | 2021-03-08 | Determine final GUI design for the Home Page and link it to the requisite pages such as "Market", "Portfolio","Account" and so forth, test for bugs.
| 8 | 2021-02-25 | 2021-03-15 | Program the Interact pages functionality and implement final designs, test security of transactions and portfolio.
| 9 | 2021-03-10 | 2021-03-22 | Continued development of Interact pages functionality, begin implementation of analysis of transactions and user investments beyond simple tracking of value.
| 10 | 2021-03-15 | 2021-03-29 | Implement Settings page that will control the appearance and functionality of the user account and allow for such features as password and information management.
| 11 | 2021-03-20 | 2021-04-05 | Finalize what features are needed for the Market pages functionality and what will be available to the user via that page and what transactions will be allowed.
| 12 | 2021-04-05 | 2021-04-12 | Polish the overall GUI presentation and design and link it to the Settings page that allows the user to customzie their experience in the application.
| 13 | 2021-04-05 | 2021-04-12 | Complete unit testing of each feature of the application, finalize security measures to protect users, and enable true transactions to begin taking place.
| 14 |  |  | TBD
| 15 |  |  | TBD
To add more milestones/activities, insert new rows above this line. This is the last instruction in this worksheet.

## Gantt chart
Gantt chart with the capability to scroll, a scrolling increment C1 increments the date range showing future activities. This is the last instruction in this worksheet. | Scrolling Increment: | 1

## About
About this workbook
Enter your data in the Project Tracker worksheet, then scroll through a visual representation of your timeline in the Gantt chart worksheet.
The position column in the Project Tracker worksheet allows you to chart milestones and activities on separate lines. You could, for instance, have two milestones/activities that start on the same day and run in parallel. They would overlap in the chart if they had the same position value. Provide two unique values to chart on separate lines. Try it! As the chart concludes, you may notice markers with no text and no duration set at a specific timeline. As the last milestone scrolls off the chart, these markers indicate the end of the milestones in the Project Tracker to chart. Simple scroll back or to the beginning to see the chartable milestones. You can scroll back and forth by entering value in 'Gantt chart!C1'
Guide for screen readers
There are 4 worksheets in this workbook. Project Tracker Gantt chart About Dynamic Chart Data (Hidden) The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you to the information in that row. Each subsequent step continues in cell A2, A3 and so on, unless otherwise explicitly directed. For example, instruction text might say “continue to cell A6” for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
This is the last instruction in this worksheet.

## Dynamic Chart Data Hidden (hidden)
Title of this worksheet is in cell B1. | Dynamic Chart Data
Table title is in cell B4. | Dynamic Data Table
Table headings are in cells B5 to E5. A note is in cell F5. This table will chart up to 5 milestones at one time. Do not modify or delete this worksheet or its contents. | milestone | date | Start-on day | duration | <--chart up to 5 milestones at a time
| Project Requirements outlined and prepared and Preliminary designs implemented via robustness diagrams and flowcharts. | 2021-01-26
| Discussion and creation of project milestones and the shape of the final product solidified by the group and submitted. | 2021-02-01
| Determine and Format all project external library requirements and keep track of all api's required and test functionality. | 2021-02-08
| Design initial GUI for the application and begin laying out activities for every page and link that will be implemented in the app. | 2021-02-08
| Implement a strict and secure account login process and link the database that will store user information to the application. Test for vulnerabilities. | 2021-02-20