## Project 1
Software Process Schedule |  |  | Architecture: Java for Android w/ CoinBase API
Project Due: 12 April, 2021
Done? | Project Details | Due By | Notes
a | Project Selection | 2021-01-26
a | Requirements & Preliminary Design | 2021-02-01
a | Project Milestones Schedule | 2021-02-08 | *milestones are subject to change*
| Detailed Design, Coding & Testing | 2021-02-15 | Begin framework. Download necessary API configurations.
| Detailed Design, Coding & Testing | 2021-02-22 | Layout all activities for every page. Impliment initial GUI design.
| Detailed Design, Coding & Testing | 2021-03-01 | Impliment and test "Login" functionality.
| Detailed Design, Coding & Testing | 2021-03-08 | Impliment and test "Home Page" functionality.
| Detailed Design, Coding & Testing | 2021-03-15 | Impliment and test "Interact Page" functionality.
| Detailed Design, Coding & Testing | 2021-03-22 | Impliment and test "Interact Page" functionality.
| Detailed Design, Coding & Testing | 2021-03-29 | Impliment and test "Settings Page" functionality
| Detailed Design, Coding & Testing | 2021-04-05 | Impliment and test "Market" functionality.
| Detailed Design, Coding & Testing | 2021-04-12 | Finalize GUI design. Finish testing all components.
| Promotional Website | 2021-04-19 | Create and launch Promotional Website for Android application.
| Capstone Conference | 2021-05-01

## Project 2
Software Process Schedule |  |  | To be completed by: Name
Deadline: Date
Done? | Project Details | Due By | Notes
a | Planning
Preparation
Task a
Task b
Task c
Task d
Paperwork
Hand-off
Follow-up

## Project 3
Software Process Schedule |  |  | To be completed by: Name
Deadline: Date
Done? | Project Details | Due By | Notes
a | Planning
Preparation
Task a
Task b
Task c
Task d
Paperwork
Hand-off
Follow-up